## Sheet1
Site | Assigned | Priority | Job description | Date posted | Notes/Updates | Current Date | Days Outstanding | Completed | Completed Date | Picture | Category
450 | Tim |  | Derelict trailers parked outside Unit E | 2022-09-07 | Met with East Rutherford police to take report. Derelict trailer on Madison Circle Drive was towed. Two trailers outside unit E must be handled by us on private property. Nicks towing notified. Will require payment to tow since material can't be salvaged. Gerry discussing directly with Nicks and Workplace (owners of derelict trailers) | 2022-10-19 | 42 |  |  | https://github.com/saferdevelopment/450/blob/main/090722/IMG_3838.JPG?raw=true | Maintenance
450 | Tim |  | Removal of 6 ash trees in front of building. | 2022-09-01 | Quotes provided from Greenwood ($7300) and Atlas ($3600). Contacted Al D Landscaping for additional quote. | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3723.jpg?raw=true | Maintenance
450 | Tim |  | Pothole filling required on Madison Circle Drive | 2022-09-01 | Responsibility of East Rutherford DPW | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3717.jpg?raw=true | Maintenance
450 | Sasha |  | Sasha to trim hedges and evergreens encroaching onto sidewalk in front of Unit A and A1 | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3722.jpg?raw=true | Maintenance
450 |  |  | Remove section of guardrail outside Unit C | 2022-09-01 |  | 2022-10-19 | 48 |  |  |  | Budgetary
450 |  |  | Holes marked outside E1 - for future repair | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3713.jpg?raw=true | Budgetary
450 |  |  | Repairs required along concete wall and pavement dropoff outside E1. Extend guard railing appx 32 feet | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3714.jpg?raw=true | Budgetary
450 | Sasha |  | Paint and caulk around doors of Unit D | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3711.jpg?raw=true | Repairs
450 |  |  | Repair or patch broken pipe / roof drain outside Unit D | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3709.jpg?raw=true | Repairs
450 |  |  | Repave entire "North Lot" (multiple holes, damage throughout). Check drawings to calculate square footage | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3708.jpg?raw=true | Budgetary
450 |  |  | Montalto to start loading dock construction at Unit B. | 2022-09-01 | Stop work order issued on 9/29 after work was partially completed. | 2022-10-19 | 48 |  |  |  | Budgetary
450 |  |  | Roof drain cover outside unit D2 should be removed/eliminated (for next year) | 2022-09-01 |  | 2022-10-19 | 48 |  |  |  | Budgetary
450 |  |  | Spray for weeds on pavement outside D2 | 2022-09-01 |  | 2022-10-19 | 48 |  |  | https://github.com/saferdevelopment/450/blob/main/090122/IMG_3702.jpg?raw=true | Maintenance
450 |  |  | ASCO fire protection testing | 2022-10-18 | Testing conducted at each riser and outdoor hydrants. May need to replace top hydrant cap in North Lot. Bolt has been stripped and hydrant was partially opened when tested. | 2022-10-19 | 1 | X |  |  | Compliance
525 |  |  | Unit 1 drain in interior loading dock is clogged. Need to snake drain | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Maintenance
525 |  |  | Stripe lines leading up to Unit 1 loading dock | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Budgetary
525 |  |  | Leak outside drip system at Unit 2 | 2022-09-02 |  | 2022-10-19 | 47 | X |  |  | Repairs
525 |  |  | Need to check all drip irrigation hoses for leaks (Carlos). Remove all weed cloth/fabric | 2022-09-02 |  | 2022-10-19 | 47 | X |  |  | Repairs
525 |  |  | Dead trees on north of property | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Maintenance
525 |  |  | Straighten parking signs - pour concrete if needed | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
525 |  |  | Seal coat and restripe north lot outside Unit 1 and Unit 2 | 2022-09-02 | Striping not completed yet | 2022-10-19 | 47 | X |  |  | Budgetary
525 |  |  | Spray for weeds in the lot | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Maintenance
525 |  |  | Crack fill entire post office lot | 2022-09-02 |  | 2022-10-19 | 47 | X |  |  | Budgetary
525 |  |  | Notify 4A tenants to remove debris in front of loading docks | 2022-09-02 |  | 2022-10-19 | 47 | X | 2022-09-08 |  | Maintenance
650 |  |  | Unit 1 tenant required to vacate unit | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Administrative
650 |  |  | Photocell issue with light at Unit 6 needs to be addressed | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
650 |  |  | Baystate - Damaged bumper blocks on middle loading dock | 2022-09-02 | Spoke with tenant about issue. They told us that the elevations are different at the three doors and they are only able to use the middle door which is causing more damage to the bumpers | 2022-10-19 | 47 |  |  |  | Repairs
650 |  | 5 | Some minor water damage on the north side wall of the building. May also need power washing. | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
650 |  |  | Some wall cracking and minor EIFS façade damage on south facing wall outside Unit 6 | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
650 |  |  | Tenant in Unit 6 (Don) notified us there is a minor leak coming from the unit heater hanging over the interior loading lock | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
969 |  |  | Need Jeff Boyer to straighten pole with mounted camera. Possibly cover exposed wires with conduit and metal box. | 2022-09-02 |  | 2022-10-19 | 47 |  |  | https://github.com/saferdevelopment/969/blob/main/090222/IMG_3728.JPG?raw=true | Repairs
969 | Tim |  | Remove all trees at entrance of property. Trees currently obstructing view of security camera. Remove dead tree in front of property. | 2022-09-02 | Quotes provided from Greenwood ($4531) and Atlas ($1800). Contacted Al D Landscaping for additional quote. | 2022-10-19 | 47 |  |  | https://github.com/saferdevelopment/969/blob/main/090222/IMG_3730.JPG?raw=true | Maintenance
969 | Tim |  | Update directory. Contact Signs by Lynn | 2022-09-02 | If family foods moving into Cooper Electric then sign content can be finalized. | 2022-10-19 | 47 |  |  |  | Maintenance
969 |  |  | Stolen cameras - Need to construct 25ft post (overall height) + two cameras on top. John H to perform work. Pole to be located on north side of shed - between shed and property line of coffin blocks. | 2022-09-02 |  | 2022-10-19 | 47 |  |  | https://github.com/saferdevelopment/969/blob/main/090222/IMG_3733.JPG?raw=true | Repairs
969 |  |  | Need to provide some roof maintenance - minor spot repairs and clean drains | 2022-09-02 |  | 2022-10-19 | 47 | X | 2022-10-06 |  | Maintenance
969 |  |  | Add flag to post | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
969 |  |  | Restripe for additional parking outside Cooper Electric | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Budgetary
969 |  |  | Create road through corner (remove coffin blocks) for easier vehicle access | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Budgetary
969 |  |  | Seal coat and restripe south lot. Spot pavement repairs. | 2022-09-02 | Restriping not completed yet. | 2022-10-19 | 47 | X | 2022-10-15 |  | Budgetary
969 |  |  | Plan for additional striping/parking outside Family Foods and Overseas Moving (east side of building) | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Budgetary
969 |  |  | Clean drainage area on east side of property | 2022-09-02 |  | 2022-10-19 | 47 | X |  |  | Maintenance
969 |  |  | Pruning required on east side of property | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Maintenance
969 |  |  | Phil needs to put continued pressure on Veola Water - resolution for water main break. | 2022-09-02 | 10/19/22 site visit showed lareger volume of water pouring out of the main and under the barrier wall. Larger volume of ponding in adjacent loading dock. | 2022-10-19 | 47 |  |  |  | Administrative
969 |  |  | Seal north lot - call Swan Seal Coating | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Budgetary
969 |  |  | Provide Albert with map of 42 truck parking spots on west lot (leased parking) | 2022-09-02 |  | 2022-10-19 | 47 | X |  |  | Administrative
969 |  |  | Boyer to inspect pump outside Panamerican loading dock | 2022-09-02 |  | 2022-10-19 | 47 |  |  |  | Repairs
969 |  |  | Top coffin block in back of parking near shed was hit by a truck. It's currently resting on top of bollard posts. Broken concrete is all over the ground. | 2022-10-19 |  | 2022-10-19 | 0 |  |  |  | Repairs
650 |  |  | Debris including used car batteries strewn outside of side door of Next Cleaners | 2022-10-19 |  | 2022-10-19 | 0 |  |  |  | Maintenance
969 |  |  | ASCO inspector pointing out fire safety issues with racking at Family Foods. Many pallets less than 18" of clearance between the rack and sprinkler. | 2022-10-19 |  | 2022-10-19 | 0 |  |  |  | Administrative